## Total
STT | Name | BackEnd | FrontEnd | Document | Desgin | Total
1 | Nguyễn Đình Hậu | 96 | 96 | 90 | 96 | 94.5
2 | Phan Tấn Lộc | 86 | 85 | 90 | 80 | 85.25
3 | Lâm Huy Hoàng | 94 | 94 | 87 | 90 | 91.25
4 | Trần Thanh Lâm | 90 | 84 | 87 | 90 | 87.75
5 | Kim Chí Khang | 88 | 80 | 87 | 87 | 85.5
| Name | Total
| Kim Chí Khang | 85.5
| Lâm Huy Hoàng | 91.25
| Nguyễn Đình Hậu | 94.5
| Phan Tấn Lộc | 85.25
| Trần Thanh Lâm | 87.75

## App Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
Feature | Function Name | Role | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Time: Begin | Time: Finish | Status | Note
Authentication | Register | Fullstack | Simple | Iteration 1 | CE181752 | Trần Thanh Lâm | Iteration 1 | 2026-01-06 | 2026-07-06 | Done
Authentication | Login | Fullstack | Simple | Iteration 1 | CE181752 | Trần Thanh Lâm | Iteration 1 | 2026-01-06 | 2026-07-06 | Done
Coordinator Management | View Coordinator List | Fullstack | Simple | Iteration 1 | CE181003 | Lâm Huy Hoàng | Iteration 1 | 2026-01-06 | 2026-07-06 | Done
Landing page | View Top rated companies | Frontend | Simple | Iteration 1 | CE180785 | Phan Tấn Lộc | Iteration 1 | 2026-01-06 | 2026-07-06 | Done
Payment Management | View Payment history | Fullstack | Simple | Iteration 1 | CE180785 | Nguyễn Đình Hậu | Iteration 1 | 2026-01-06 | 2026-07-06 | Done
Subscription Management | View and Manage Subscription | Fullstack | Simple | Iteration 1 | CE180785 | Nguyễn Đình Hậu | Iteration 1 | 2026-01-06 | 2026-07-06 | Done
Company Management | Add Company Information | Fullstack | Medium | Iteration 1 | CE180324 | Kim Chí Khang | Iteration 1 | 2026-01-06 | 2026-07-06 | Incomplete
Company Management | Add Business License | Fullstack | Medium | Iteration 1 | CE180324 | Kim Chí Khang | Iteration 1 | 2026-01-06 | 2026-07-06 | Incomplete
Coordinator Management | Create Coordinator Account | Fullstack | Medium | Iteration 1 | CE181003 | Lâm Huy Hoàng | Iteration 1 | 2026-01-06 | 2026-07-06 | Incomplete
Payment Management | Pay SaaS Plan | Fullstack | Medium | Iteration 1 | CE180785 | Nguyễn Đình Hậu | Iteration 1 | 2026-01-06 | 2026-07-06 | Incomplete
Profile Management | Add Profile information | Fullstack | Medium | Iteration 1 | CE180324 | Kim Chí Khang | Iteration 1 | 2026-01-06 | 2026-07-06 | Incomplete
Registration Moderation | View Registrations | Fullstack | Simple | Iteration 1 | CE171503 | Phan Tấn Lộc | Iteration 1 | 2026-01-06 | 2026-07-06 | Incomplete
Registration Moderation | View Registrations Detail | Fullstack | Simple | Iteration 1 | CE171503 | Phan Tấn Lộc | Iteration 1 | 2026-01-06 | 2026-07-06 | Incomplete
Registration Moderation | Approve/Reject Company | Fullstack | Simple | Iteration 1 | CE171503 | Phan Tấn Lộc | Iteration 1 | 2026-01-06 | 2026-07-06 | Incomplete
Authentication | Email verification | Fullstack | Simple | Iteration 1 | CE181752 | Trần Thanh Lâm | Iteration 1 | 2026-01-06 | 2026-07-06 | Rework
Contract Management | View My Contracts | Fullstack | Medium | Iteration 2 | CE181003 | Lâm Huy Hoàng | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Contract Management | View My Contract Detail | Fullstack | Medium | Iteration 2 | CE181003 | Lâm Huy Hoàng | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Contract Management | View Contracts | Fullstack | Medium | Iteration 2 | CE180785 | Nguyễn Đình Hậu | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Contract Management | View Contract Detail | Fullstack | Medium | Iteration 2 | CE180785 | Nguyễn Đình Hậu | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Contract Management | Upload Physical Contract | Fullstack | Medium | Iteration 2 | CE180785 | Nguyễn Đình Hậu | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Contract Management | Confirm Contract By Company | Fullstack | Medium | Iteration 2 | CE180785 | Nguyễn Đình Hậu | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Contract Management | Confirm Contract By Customer | Fullstack | Medium | Iteration 2 | CE181003 | Lâm Huy Hoàng | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Registration Moderation | View Registrations | Fullstack | Simple | Iteration 2 | CE171503 | Phan Tấn Lộc | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Registration Moderation | View Registrations Detail | Fullstack | Simple | Iteration 2 | CE171503 | Phan Tấn Lộc | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Registration Moderation | Approve/Reject Company | Fullstack | Simple | Iteration 2 | CE171503 | Phan Tấn Lộc | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Company Management | View Companies | Fullstack | Medium | Iteration 2 | CE171503 | Phan Tấn Lộc | Iteration 2 | 2026-08-06 | 14-06-2026 | Incomplete
Company Management | Search & Filter companies | Fullstack | Medium | Iteration 2 | CE171503 | Phan Tấn Lộc | Iteration 2 | 2026-08-06 | 14-06-2026 | Incomplete
Company Management | View Company Details | Fullstack | Medium | Iteration 2 | CE171503 | Phan Tấn Lộc | Iteration 2 | 2026-08-06 | 14-06-2026 | Done
Service Request Management | Send Service request | Fullstack | Medium | Iteration 2 | CE180324 | Kim Chí Khang | Iteration 2 | 2026-08-06 | 14-06-2026 | Incomplete
Service Request Management | Update service quotation (company) | Fullstack | Medium | Iteration 2 | CE180324 | Kim Chí Khang | Iteration 2 | 2026-08-06 | 14-06-2026 | Incomplete
Service Request Management | Confirm/Deny quotation (customer) | Fullstack | Medium | Iteration 2 | CE180324 | Kim Chí Khang | Iteration 2 | 2026-08-06 | 14-06-2026 | Incomplete
Coordinator Management | Add Coordinator Account | Fullstack | Medium | Iteration 2 | CE181003 | Lâm Huy Hoàng | Iteration 2 | 2026-01-06 | 2026-07-06 | Rework
Guard Management | Create Guard Account | Fullstack | Medium | Iteration 2 | CE181752 | Trần Thanh Lâm | Iteration 2 | 2026-08-06 | 14-06-2026 | Rework
Guard Management | View Guards | Fullstack | Medium | Iteration 2 | CE181752 | Trần Thanh Lâm | Iteration 2 | 2026-08-06 | 14-06-2026 | Rework
Shift Management | View work shifts | Fullstack | Medium | Iteration 2 | CE181752 | Trần Thanh Lâm | Iteration 2 | 2026-08-06 | 14-06-2026 | Rework
Authentication | Logout | Fullstack | Medium | Iteration 3 | CE181752 | Trần Thanh Lâm | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Company Management | Add Company Information | Fullstack | Medium | Iteration 3 | CE180324 | Kim Chí Khang | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Company Management | Add Business License | Fullstack | Medium | Iteration 3 | CE180324 | Kim Chí Khang | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Company Management | View Companies | Fullstack | Medium | Iteration 3 | CE171503 | Phan Tấn Lộc | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Company Management | Search & Filter companies | Fullstack | Medium | Iteration 3 | CE171503 | Phan Tấn Lộc | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Profile Management | Add Profile information | Fullstack | Medium | Iteration 3 | CE180324 | Kim Chí Khang | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Review Management | Send Service Review | Fullstack | Medium | Iteration 3 | CE181003 | Lâm Huy Hoàng | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Service Request Management | view my requests | Fullstack | Medium | Iteration 3 | CE180324 | Kim Chí Khang | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Service Request Management | view my request detail | Fullstack | Medium | Iteration 3 | CE180324 | Kim Chí Khang | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Service Request Management | view requests | Fullstack | Medium | Iteration 3 | CE180785 | Nguyễn Đình Hậu | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Service Request Management | view request detail | Fullstack | Medium | Iteration 3 | CE180785 | Nguyễn Đình Hậu | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Service Request Management | View Bookings | Fullstack | Medium | Iteration 3 | CE180785 | Nguyễn Đình Hậu | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Service Request Management | View Booking Detail | Fullstack | Medium | Iteration 3 | CE180785 | Nguyễn Đình Hậu | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Shift Management | View my work shift | Fullstack | Medium | Iteration 3 | CE181752 | Trần Thanh Lâm | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Shift Management | View work shift Detail | Fullstack | Medium | Iteration 3 | CE181752 | Trần Thanh Lâm | Iteration 3 | 15-06-2026 | 21-06-2026 | Done
Company Management | View Company Profile | Fullstack | Medium | Iteration 3 | CE171503 | Phan Tấn Lộc | Iteration 3 | 15-06-2026 | 21-06-2026 | Incomplete
Company Management | Add Company Service | Fullstack | Medium | Iteration 3 | CE171503 | Phan Tấn Lộc | Iteration 3 | 15-06-2026 | 21-06-2026 | Incomplete
Review Management | View Company reviews | Fullstack | Medium | Iteration 3 | CE181003 | Lâm Huy Hoàng | Iteration 3 | 15-06-2026 | 21-06-2026 | Rework
Shift Management | Create work shift | Fullstack | Medium | Iteration 3 | CE181752 | Trần Thanh Lâm | Iteration 3 | 15-06-2026 | 21-06-2026 | Rework
Shift Management | Check-in work shift | Fullstack | Medium | Iteration 3 | CE181752 | Trần Thanh Lâm | Iteration 3 | 15-06-2026 | 21-06-2026 | Rework
Chat System | Chat with customer | Fullstack | Medium | Iteration 4 | CE181003 | Lâm Huy Hoàng | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Chat System | Chat with company | Fullstack | Medium | Iteration 4 | CE181003 | Lâm Huy Hoàng | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Company Management | View Company Profile (Company) | Fullstack | Medium | Iteration 4 | CE171503 | Phan Tấn Lộc | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Company Management | Add Company Service | Fullstack | Medium | Iteration 4 | CE171503 | Phan Tấn Lộc | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Contract Management | Complete Contract (customer) | Fullstack | Medium | Iteration 4 | CE180785 | Nguyễn Đình Hậu | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Registration Moderation | View Publish Request list | Fullstack | Medium | Iteration 4 | CE171503 | Phan Tấn Lộc | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Review Management | View Review list (Company) | Fullstack | Medium | Iteration 4 | CE181752 | Trần Thanh Lâm | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Service Request Management | Update service quotation (company) | Fullstack | Medium | Iteration 4 | CE180324 | Kim Chí Khang | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Service Request Management | Confirm/Deny quotation (customer) | Fullstack | Medium | Iteration 4 | CE180324 | Kim Chí Khang | Iteration 4 | 22-06-2026 | 28-06-2026 | Done
Profile Management | View Profile Detail (Customer) | Fullstack | Medium | Iteration 4 | CE180324 | Kim Chí Khang | Iteration 4 | 22-06-2026 | 28-06-2026 | Incomplete
Profile Management | Update Profile (Customer) | Fullstack | Medium | Iteration 4 | CE180324 | Kim Chí Khang | Iteration 4 | 22-06-2026 | 28-06-2026 | Incomplete
Registration Moderation | Approve/Reject publish request | Fullstack | Medium | Iteration 4 | CE171503 | Phan Tấn Lộc | Iteration 4 | 22-06-2026 | 28-06-2026 | Incomplete
Company Management | Edit Company Profile | Fullstack | Medium | Iteration 4 | CE181752 | Trần Thanh Lâm | Iteration 4 | 22-06-2026 | 28-06-2026 | Rework
Registration Moderation | Send Publish Request | Fullstack | Medium | Iteration 4 | CE180785 | Nguyễn Đình Hậu | Iteration 4 | 22-06-2026 | 28-06-2026 | Rework
Service Request Management | Send Service request | Fullstack | Medium | Iteration 4 | CE180324 | Kim Chí Khang | Iteration 4 | 22-06-2026 | 28-06-2026 | Rework
Authentication | Email verfication | Fullstack | Simple | Iteration 5 | CE181752 | Trần Thanh Lâm | Iteration 5 | 29-06-2026 | 2026-05-07 | Done | Add redirect to page by role after verifying success
Company Management | Edit Company Profile | Fullstack | Medium | Iteration 5 | CE181752 | Trần Thanh Lâm | Iteration 5 | 29-06-2026 | 2026-05-07 | Done | Update email filed should not be updated, should be view-only
Coordinator Management | Create Coordinator Account | Fullstack | Medium | Iteration 5 | CE181003 | Lâm Huy Hoàng | Iteration 5 | 29-06-2026 | 2026-05-07 | Done
Guard Management | Create Guard Account | Fullstack | Medium | Iteration 5 | CE181752 | Trần Thanh Lâm | Iteration 5 | 29-06-2026 | 2026-05-07 | Done | Add upload CCCD and select ward and city
Guard Management | View Guards | Fullstack | Medium | Iteration 5 | CE181752 | Trần Thanh Lâm | Iteration 5 | 29-06-2026 | 2026-05-07 | Done | Add page panigation and working status
Payment Management | Pay SaaS Plan | Fullstack | Medium | Iteration 5 | CE180785 | Nguyễn Đình Hậu | Iteration 5 | 29-06-2026 | 2026-05-07 | Done | Integrated QR code payment for SaaS plan
Profile Management | View Profile Detail | Fullstack | Medium | Iteration 5 | CE180324 | Kim Chí Khang | Iteration 5 | 29-06-2026 | 2026-05-07 | Done
Registration Moderation | View Publish Request Detail | Fullstack | Medium | Iteration 5 | CE171503 | Phan Tấn Lộc | Iteration 5 | 29-06-2026 | 2026-05-07 | Done
Registration Moderation | Approve/Reject publish request | Fullstack | Medium | Iteration 5 | CE171503 | Phan Tấn Lộc | Iteration 5 | 29-06-2026 | 2026-05-07 | Done
Registration Moderation | Send Publish Request | Fullstack | Medium | Iteration 5 | CE180785 | Nguyễn Đình Hậu | Iteration 5 | 29-06-2026 | 2026-05-07 | Done
Review Management | View Company reviews | Fullstack | Medium | Iteration 5 | CE181003 | Lâm Huy Hoàng | Iteration 5 | 29-06-2026 | 2026-05-07 | Done
Service Request Management | Send Service request | Fullstack | Medium | Iteration 5 | CE180324 | Kim Chí Khang | Iteration 5 | 29-06-2026 | 2026-05-07 | Done
Shift Management | Create work shift | Fullstack | Medium | Iteration 5 | CE181752 | Trần Thanh Lâm | Iteration 5 | 29-06-2026 | 2026-05-07 | Done | Add automatic shift scheduling for weekly, monthly, and yearly periods.
Shift Management | Check-in work shift | Fullstack | Medium | Iteration 5 | CE181752 | Trần Thanh Lâm | Iteration 5 | 29-06-2026 | 2026-05-07 | Done | Implement checkin with image and absent, late logic
Shift Management | View work shifts | Fullstack | Medium | Iteration 5 | CE181752 | Trần Thanh Lâm | Iteration 5 | 29-06-2026 | 2026-05-07 | Done | Extend shift view to one year ahead.
Profile Management | Update Profile | Fullstack | Medium | Iteration 5 | CE180324 | Kim Chí Khang | Iteration 5 | 29-06-2026 | 2026-05-07 | Incomplete
Payment Management | View Bank Account | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Payment Management | Add Bank Account | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Payment Management | Update Bank Account | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Payment Management | Delete Bank Account | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Report Management | Submit report | Fullstack | Medium | Iteration 6 | CE171503 | Phan Tấn Lộc | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Report Management | View reports | Fullstack | Medium | Iteration 6 | CE171503 | Phan Tấn Lộc | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Report Management | Update reports | Fullstack | Medium | Iteration 6 | CE171503 | Phan Tấn Lộc | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Report Management | View my reports | Fullstack | Medium | Iteration 6 | CE171503 | Phan Tấn Lộc | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Report Management | View my report detail | Fullstack | Medium | Iteration 6 | CE171503 | Phan Tấn Lộc | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Shift management | Dispatch replacement guard | Fullstack | Medium | Iteration 6 | CE181752 | Trần Thanh Lâm | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Guard management | View guard detail | Fullstack | Medium | Iteration 6 | CE181752 | Trần Thanh Lâm | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Coordinator Management | View Coordinator detail | Fullstack | Medium | Iteration 6 | CE181003 | Lâm Huy Hoàng | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Coordinator Management | Search & Filter Coordinator | Fullstack | Medium | Iteration 6 | CE181003 | Lâm Huy Hoàng | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Guard management | Update Guard Profile | Fullstack | Medium | Iteration 6 | CE181752 | Trần Thanh Lâm | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Coordinator Management | Update Coordinator Profile | Fullstack | Medium | Iteration 6 | CE181003 | Lâm Huy Hoàng | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Service Request Management | Create Request Verification | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Service Request Management | View Request Verifications | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Service Request Management | View Request Verification Detail | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Service Request Management | Update Request Verification | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Service Request Management | Approve/Reject Request Verification | Fullstack | Medium | Iteration 6 | CE180785 | Nguyễn Đình Hậu | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Contract Management | Add guard into contract | Fullstack | Medium | Iteration 6 | CE181752 | Trần Thanh Lâm | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Guard management | Search & Filter Guard | Fullstack | Medium | Iteration 6 | CE180324 | Kim Chí Khang | Iteration 6 | 2026-06-07 | 13-07-2026 | Done
Registration Moderation | Register company | Fullstack | Medium | Iteration 6 | CE180324 | Kim Chí Khang | Iteration 6 | 2026-06-07 | 13-07-2026 | Done | Modify register from sign up account
Registration Moderation | Approve/Reject publish request | Fullstack | Medium | Iteration 6 | CE171503 | Phan Tấn Lộc | Iteration 6 | 2026-06-07 | 13-07-2026 | Done | Add Send an email confirming the publish status.
Language Switching | Change Language | Fullstack | Medium | Iteration 7 | CE180785 | Nguyễn Đình Hậu | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Contract Management | Export Contract | Fullstack | Medium | Iteration 7 | CE180785 | Nguyễn Đình Hậu | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Subscription Management | View Plans By Admin | Fullstack | Medium | Iteration 7 | CE171503 | Phan Tấn Lộc | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Subscription Management | Update Plan | Fullstack | Medium | Iteration 7 | CE171503 | Phan Tấn Lộc | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Subscription Management | Add Plan | Fullstack | Medium | Iteration 7 | CE171503 | Phan Tấn Lộc | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Subscription Management | Delete Plan | Fullstack | Medium | Iteration 7 | CE171503 | Phan Tấn Lộc | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Service Management | Add Services | Fullstack | Medium | Iteration 7 | CE181003 | Lâm Huy Hoàng | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Service Management | Update Services | Fullstack | Medium | Iteration 7 | CE181003 | Lâm Huy Hoàng | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Service Management | View Services | Fullstack | Medium | Iteration 7 | CE181003 | Lâm Huy Hoàng | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Service Management | Delete Services | Fullstack | Medium | Iteration 7 | CE181003 | Lâm Huy Hoàng | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Account Management | View Accounts | Fullstack | Medium | Iteration 7 | CE180324 | Kim Chí Khang | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Account Management | Search and filter Account | Fullstack | Medium | Iteration 7 | CE180324 | Kim Chí Khang | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Authentication | Reset Password | Fullstack | Medium | Iteration 7 | CE180324 | Kim Chí Khang | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Payment Management | View Subscription Payments | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Account Management | Ban Account | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Company Dashboard | View Total Active Contracts | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Company Dashboard | View Total Pending Reports | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Company Dashboard | View Total On-Duty Guards | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Admin Dashboard | View Pending Approval Requests | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Admin Dashboard | View Plan Distribution | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Admin Dashboard | View total users | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Admin Dashboard | View Total Revenue | Fullstack | Medium | Iteration 7 | CE181752 | Trần Thanh Lâm | Iteration 7 | 14-07-2026 | 19-07-2026 | Done
Contract Management | Edit Service Request | Fullstack | Medium | Iteration 8 | CE171503 | Phan Tấn Lộc | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Registration Moderation | View register request | Fullstack | Medium | Iteration 8 | CE181003 | Lâm Huy Hoàng | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Registration Moderation | Update register request | Fullstack | Medium | Iteration 8 | CE181003 | Lâm Huy Hoàng | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Authentication | Forgot password | Fullstack | Medium | Iteration 8 | CE180324 | Kim Chí Khang | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Guard management | View Guard Performance | Fullstack | Medium | Iteration 8 | CE181752 | Trần Thanh Lâm | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Authentication | Test all function | Testing | Medium | Iteration 8 | CE181752 | Trần Thanh Lâm | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Company Management | Test part of functions | Testing | Medium | Iteration 8 | CE180785 | Nguyễn Đình Hậu | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Registration Moderation | Test all function | Testing | Medium | Iteration 8 | CE171503 | Phan Tấn Lộc | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Subscription Management | Test all function | Testing | Medium | Iteration 8 | CE180324 | Kim Chí Khang | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Payment Management | Test all function | Testing | Medium | Iteration 8 | CE180785 | Nguyễn Đình Hậu | Iteration 8 | 20-07-2026 | 26-07-2026 | Done
Company Management | View Companies By Admin | Fullstack | Medium | Iteration 9 | CE180324 | Kim Chí Khang | Iteration 9 | 27-07-2026 | 2026-02-08 | Done
Contract Management | Export Contract | Fullstack | Medium | Iteration 9 | CE180785 | Nguyễn Đình Hậu | Iteration 9 | 27-07-2026 | 2026-02-08 | Done | Update: add input form before exporting contract to word
Service Request Management | Update service quotation (company) | Fullstack | Medium | Iteration 9 | CE180785 | Nguyễn Đình Hậu | Iteration 9 | 27-07-2026 | 2026-02-08 | Done | Update: add more quotation options
Contract Management | Add guard into contract | Fullstack | Medium | Iteration 9 | CE181752 | Trần Thanh Lâm | Iteration 9 | 27-07-2026 | 2026-02-08 | Done | Update: Remove the mandatory security assignment; making it optional is fine.
Coordinator Dashboard | View past shifts | Fullstack | Medium | Iteration 9 | CE181752 | Trần Thanh Lâm | Iteration 9 | 27-07-2026 | 2026-02-08 | Done
Coordinator Dashboard | View Available Guards | Fullstack | Medium | Iteration 9 | CE181752 | Trần Thanh Lâm | Iteration 9 | 27-07-2026 | 2026-02-08 | Done
Coordinator Dashboard | View Current & Upcoming Shifts | Fullstack | Medium | Iteration 9 | CE181752 | Trần Thanh Lâm | Iteration 9 | 27-07-2026 | 2026-02-08 | Done
Coordinator Dashboard | View Total Incident Reports Today | Fullstack | Medium | Iteration 9 | CE181752 | Trần Thanh Lâm | Iteration 9 | 27-07-2026 | 2026-02-08 | Done
Coordinator Management | Create Coordinator Account | Fullstack | Medium | Iteration 9 | CE181003 | Lâm Huy Hoàng | Iteration 9 | 27-07-2026 | 2026-02-08 | Done | Update: Limit to exactly 1 coordinator.
Company Management | Add Company Information | Fullstack | Medium | Iteration 9 | CE181003 | Lâm Huy Hoàng | Iteration 9 | 27-07-2026 | 2026-02-08 | Done | Update: Require min 2 extra images for company registration.
Service Request Management | Send Service request | Fullstack | Medium | Iteration 9 | CE180324 | Kim Chí Khang | Iteration 9 | 27-07-2026 | 2026-02-08 | Done | Update: Add the facility name and sector to the booking, and make profile information mandatory when creating a request.
Company Management | Add Company Service | Fullstack | Medium | Iteration 9 | CE171503 | Phan Tấn Lộc | Iteration 9 | 27-07-2026 | 2026-02-08 | Done | Update: Improve Company Service Management UI with Price Formatting and Service Display
Service Request Management | Test all function | Testing | Medium | Iteration 9 | CE180324 | Kim Chí Khang | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Shift Management | Test all function | Testing | Medium | Iteration 9 | CE181752 | Trần Thanh Lâm | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Guard management | Test all function | Testing | Medium | Iteration 9 | CE181752 | Trần Thanh Lâm | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Service Management | Test all function | Testing | Medium | Iteration 9 | CE181003 | Lâm Huy Hoàng | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Account Management | Test all function | Testing | Medium | Iteration 9 | CE171503 | Phan Tấn Lộc | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Profile Management | Test all function | Testing | Medium | Iteration 9 | CE180324 | Kim Chí Khang | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Registration Moderation | Test all function | Testing | Medium | Iteration 9 | CE180785 | Nguyễn Đình Hậu | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Chat System | Test all function | Testing | Medium | Iteration 9 | CE180785 | Nguyễn Đình Hậu | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Coordinator management | Test all function | Testing | Medium | Iteration 9 | CE181003 | Lâm Huy Hoàng | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Review Management | Test all function | Testing | Medium | Iteration 9 | CE181003 | Lâm Huy Hoàng | Iteration 9 | 27-07-2026 | 2026-01-08 | Done
Authentication | Login | Fullstack | Simple | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: trim password before signing in
Authentication | Register | Fullstack | Simple | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: trim password and confirm password before signing up
Shift Management | Request Shift Substitute | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done
Shift Management | View Shift Substitute Requests | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done
Shift Management | Approve/Reject shift Substitute | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done
Shift Management | Create work shift | Fullstack | Simple | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: allow shifts over 8h, mark as overtime instead of blocking
Contract Management | View Contract Detail | Fullstack | Simple | Iteration 10 | CE180785 | Nguyễn Đình Hậu | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: snapshot company name at contract creation to prevent changes from affecting old contracts
Guard management | Send Verification Guard | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done
Guard management | Approve/Reject guard profile | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done
Guard Management | Update Guard Profile | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: add height, weight, health certificate, skill certificates, and notable skills fields
Guard Management | Update Guard Profile | Fullstack | Medium | Iteration 10 | CE181003 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Add: allow guard to self-update their own profile
Service Request Management | Update service quotation (company) | Fullstack | Medium | Iteration 10 | CE180324 | Nguyễn Đình Hậu | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: add discount percentage to quotation calculation
Contract Management | View Contract Detail | Fullstack | Medium | Iteration 10 | CE180785 | Nguyễn Đình Hậu | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: display full price breakdown (unit price × hours, discount, final amount)
Company Management | Search & Filter companies | Fullstack | Medium | Iteration 10 | CE171503 | Phan Tấn Lộc | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: add min/max price range filter to company search
Shift Management | View work shifts | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Update: show overtime indicator on shifts and overtime hours in guard performance
Company Management | Search & Filter companies | Fullstack | Medium | Iteration 10 | CE181003 | Lâm Huy Hoàng | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Add: find nearby companies using current location
Company Management | Compare companies | Fullstack | Medium | Iteration 10 | CE181003 | Kim Chí Khang | Iteration 10 | 2026-08-08 | 13-08-2026 | Done | Add: Compare two companies about price, rating
Guard management | Send Verification Guard | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done
Guard management | View Personal Guard Profile | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done
Guard management | Approve/Reject guard profile | Fullstack | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 13-08-2026 | Done
Authentication | Test part of functions | Testing | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | Login, Register
Shift Management | Test part of functions | Testing | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | Create work shift, View work shift
Guard Management | Test part of functions | Testing | Medium | Iteration 10 | CE181003 | Lâm Huy Hoàng | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | Update Guard Profile, Send Verification Guard, Approve/Reject guard profile
Contract Management | Test part of functions | Testing | Medium | Iteration 10 | CE180785 | Nguyễn Đình Hậu | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | View Contract Detail
Service Request Management | Test part of functions | Testing | Medium | Iteration 10 | CE180324 | Kim Chí Khang | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | Update service quotation
Admin Dashboard | Test part of functions | Testing | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | view total revenue, View total users, View Plan Distribution, View pending task
Coordinator Dashboard | Test part of functions | Testing | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | View Total Incident Reports Today, View Current & Upcoming Shifts, View Available Guards, View past shifts
Company dashboard | Test part of functions | Testing | Medium | Iteration 10 | CE181752 | Trần Thanh Lâm | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | View Total On-Duty Guards, view total active contracts, View Total Pending Reports
Company Management | Test part of functions | Testing | Medium | Iteration 10 | CE171503 | Phan Tấn Lộc | Iteration 10 | 2026-08-08 | 14-08-2026 | Done | Search & Filter companies
Contract Management | View My Contracts | Fullstack | Medium | Iteration 11 | CE181003 | Lâm Huy Hoàng | Iteration 11 | 2026-06-09 | 13-09-2026 | To Do | Modify code according to the updated data table
Contract Management | View My Contract Detail | Fullstack | Medium | Iteration 11 | CE181003 | Lâm Huy Hoàng | Iteration 11 | 2026-06-09 | 13-09-2026 | To Do | Modify code according to the updated data table
Contract Management | View Contracts | Fullstack | Medium | Iteration 11 | CE180785 | Nguyễn Đình Hậu | Iteration 11 | 2026-06-09 | 13-09-2026 | To Do | Modify code according to the updated data table
Contract Management | View Contract Detail | Fullstack | Medium | Iteration 11 | CE180785 | Nguyễn Đình Hậu | Iteration 11 | 2026-06-09 | 13-09-2026 | To Do | Modify code according to the updated data table
Shift Management | Create work shift | Fullstack | Medium | Iteration 11 | CE181752 | Trần Thanh Lâm | Iteration 11 | 2026-06-09 | 13-09-2026 | To Do | Modify code according to the updated data table
Shift Management | View Contract Shift Schedule | Fullstack | Medium | Iteration 11 | CE181752 | Trần Thanh Lâm | Iteration 11 | 2026-06-09 | 13-09-2026 | To Do
dashboard -> feature khác

## Docs Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
Function Name | Feature | Complexity | In-charge Full Name | Time: Begin | Time: Finish | Time: Resit | Note | Roll Number | Full Name
Report1 | Overview | Simple | Phan Tấn Lộc | 14/05/2026 | 15/05/2026 | 15/05/2026 |  | CE171602 | PhuocNDT
Report1 | Product Background | Medium | Trần Thanh Lâm | 14/05/2026 | 15/05/2026 | 15/05/2026 |  | CE170038 | SaoBC
Report1 | Existing Systems | Medium | Kim Chí Khang | 14/05/2026 | 15/05/2026 | 15/05/2026 |  | CE171129 | DinhTV
Report1 | Business Opportunity | Medium | Lâm Huy Hoàng | 14/05/2026 | 15/05/2026 | 15/05/2026 |  | CA171336 | ThanhLP
Report1 | Software Product Vision | Medium | Lâm Huy Hoàng | 14/05/2026 | 15/05/2026 | 15/05/2026 |  | CE170133 | ThuanCH
Report1 | Project Scope & Limitations | Medium | Nguyễn Đình Hậu | 14/05/2026 | 15/05/2026 | 15/05/2026
Report2 | Overview | Simple | Phan Tấn Lộc | 16/05/2026 | 21/05/2026 | 21/05/2026
Report2 | Management Approach | Medium | Trần Thanh Lâm | 16/05/2026 | 21/05/2026 | 21/05/2026
Report2 | Project Organization | Medium | Lâm Huy Hoàng | 16/05/2026 | 21/05/2026 | 21/05/2026
Report2 | Project Deliverables | Medium | Kim Chí Khang | 16/05/2026 | 21/05/2026 | 21/05/2026
Report2 | Responsibility Assignments | Medium | Kim Chí Khang | 16/05/2026 | 21/05/2026 | 21/05/2026
Report2 | Project Communications | Medium | Nguyễn Đình Hậu | 16/05/2026 | 21/05/2026 | 21/05/2026
Report2 | Configuration Management | Medium | Nguyễn Đình Hậu | 16/05/2026 | 21/05/2026 | 21/05/2026
Report3 | Product Overview | Medium | Phan Tấn Lộc | 22/5/2026 | 28/5/2026 | 28/5/2026
Report3 | User Requirements | Medium | Phan Tấn Lộc | 22/5/2026 | 28/5/2026 | 28/5/2026
Report3 | Use Case Specification | Medium | Phan Tấn Lộc | 22/5/2026 | 28/5/2026 | 28/5/2026
Report3 | Functional Requirements | Medium | Lâm Huy Hoàng | 22/5/2026 | 28/5/2026 | 28/5/2026
Report3 | Non-Functional Requirements | Medium | Nguyễn Đình Hậu | 22/5/2026 | 28/5/2026 | 28/5/2026
Report3 | Requirement Appendix | Medium | Trần Thanh Lâm | 22/5/2026 | 28/5/2026 | 28/5/2026
Report4 | System Design | Medium | Nguyễn Đình Hậu | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Database Design | Medium | Nguyễn Đình Hậu | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Class diagram) | Complex | Trần Thanh Lâm | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Class diagram) | Complex | Lâm Huy Hoàng | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Class diagram) | Complex | Lâm Huy Hoàng | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Class diagram) | Complex | Nguyễn Đình Hậu | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Class diagram) | Complex | Nguyễn Đình Hậu | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Sequence) | Complex | Trần Thanh Lâm | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Sequence) | Complex | Lâm Huy Hoàng | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Sequence) | Complex | Lâm Huy Hoàng | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Sequence) | Complex | Nguyễn Đình Hậu | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Detailed Design (Sequence) | Complex | Nguyễn Đình Hậu | 28/5/2026 | 2026-04-06 | 2026-04-06
Report4 | Class Specification | Medium | Kim Chí Khang | 28/5/2026 | 2026-04-06 | 2026-04-06
Report5 | Scope of Testing | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5 | Test Strategy | Medium | Kim Chí Khang | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5 | Test Plan | Medium | Lâm Huy Hoàng | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5 | Test Cases | Medium | Phan Tấn Lộc | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5 | Test Reports | Medium | Trần Thanh Lâm | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | isValidDateKey | Medium | Trần Thanh Lâm | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | formatPrice | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | checkTimeOverlap | Medium | Trần Thanh Lâm | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | validateBookingUpdateStatusData | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | calculateHoursFromSlot | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | validateAssignGuardsRules | Medium | Trần Thanh Lâm | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | validateCustomerSignatureEligibility | Medium | Lâm Huy Hoàng | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | validateContractExpiration | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | validatePaymentPayload | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Unit Test) | validateWebhookTransactionCode | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Authentication | Medium | Trần Thanh Lâm | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Shift Management | Medium | Trần Thanh Lâm | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Guard management | Medium | Trần Thanh Lâm | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Chat System | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Coordinator management | Medium | Lâm Huy Hoàng | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Review Management | Medium | Lâm Huy Hoàng | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Registration Moderation | Medium | Phan Tấn Lộc | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Payment Management | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Company Management | Medium | Nguyễn Đình Hậu | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Subscription Management | Medium | Kim Chí Khang | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Service Request Management | Medium | Kim Chí Khang | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Service Management | Medium | Lâm Huy Hoàng | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Account Management | Medium | Phan Tấn Lộc | 2026-06-04 | 18/6/2026 | 18/6/2026
Report5(Test Report) | Profile Management | Medium | Kim Chí Khang | 2026-06-04 | 18/6/2026 | 18/6/2026
Report6 | Deliverable Package | Medium | Nguyễn Đình Hậu | 20/7/2026 | 23/7/2026 | 2026-04-08
Report6 | System Requirements | Medium | Nguyễn Đình Hậu | 20/7/2026 | 23/7/2026 | 2026-04-08
Report6 | Installation Guide | Medium | Phan Tấn Lộc | 20/7/2026 | 23/7/2026 | 2026-04-08
Report6 | User Manual | Medium | Trần Thanh Lâm | 20/7/2026 | 23/7/2026 | 2026-04-08
Report6 | Website | Medium | Kim Chí Khang | 20/7/2026 | 23/7/2026 | 2026-04-08
Report7 | Create, Format | Medium | Phan Tấn Lộc | 23/7/2026 | 2026-04-08 | 2026-04-08
Report7 | Paper | Simple | Nguyễn Đình Hậu | 23/7/2026 | 2026-04-08 | 2026-04-08

## Planned Code Iteration Time
Planned Code Iteration | Start | End
Iteration 1 | 2026-01-06 | 2026-07-06
Iteration 2 | 2026-08-06 | 14-06-2026
Iteration 3 | 15-06-2026 | 21-06-2026
Iteration 4 | 22-06-2026 | 28-06-2026
Iteration 5 | 29-06-2026 | 2026-05-07
Iteration 6 | 2026-06-07 | 13-07-2026
Iteration 7 | 14-07-2026 | 19-07-2026
Iteration 8 | 20-07-2026 | 26-07-2026
Iteration 9 | 27-07-2026 | 2026-02-08
Iteration 10 | 2026-08-08 | 15-08-2026